## Sheet1
Unique ID | User story | Story Points | Assignee | Reviewers 1 | Reviewers 2
1 | SMS -Front End | 8 | Rawan | Farah | Aliaa
1.1 | Workspace Accessing form & reviewing it | 8 | Farah | Sama | Hana
1.2 | Payment System | 8 | Sama | Hana | Aliaa
1.3 | Upload documents | 8 | Mariam | Aliaa | Hana
1.4 | Authentication & Authorization | 8 | Sarah | Sama | Hana
1.5 | As a logged in admin I should be able to search all cases to be able to view case details - Front End | 5 | Mohamed Ghalab | Farah | Sama
1.6 | Add about Us , Contact Us &Facebook | 5 | Eyad | Aliaa | Farah
1.7 | Front End modification | 8 | Aliaa | Sama | Farah
1.8 | As a logged in investor i should be able to view my other finalized and pending companies on my company's pages to be able to view their information - Front End | 8 | Hana | Hana | Farah
1.9 | Notification System - Front end | 8 | Norhan | Aliaa | Sama
2 | As a logged in reviewer i should be able to access a shared workspace with the other reviewers to be able to see all available unlocked cases |  | Menna | Sama | Farah