## Sheet1
Unique ID | User story | Story Points | Assignee | Reviewers 1 | Reviewers 2
1 | As a logged in investor i should be able to check notifications to be able to check updates on my case | 5 | Sarah | Sama | Aliaa
1.1 | As a logged in reviewer l should be able to notify investor to pay the fees when the form is approved to finalize the process. | 5 | Eyad | Sama | Aliaa
1.2 | As a logged in investor i should be able to view my other finalized and pending companies on my company's pages to be able to view their information | 5 | Hana | Sama | Aliaa
1.3 | As a logged in lawyer i should be able to access a shared workspace with the other lawyers to be able to see all available unlocked cases | 5 | Rawan | Sama | Aliaa
1.4 | As a logged in lawyer i should be able to open any of my cases to become locked and move out of the to shared workspace | 3 | Norhan | Sama | Aliaa
1.5 | As a logged in lawyer i should be able to close any of my cases to become unlocked and move in to the shared workspace | 3 | Norhan | Sama | Aliaa
1.6 | As a logged in reviewer l should be able to filter all of my cases by either “Case Creation ID” or “Case Creation Date” to sort his/her tasks. | 5 | menna | Sama | Aliaa
1.7 | As a logged in admin I should be able to search all cases to be able to view case details | 5 | Ghallab | Sama | Aliaa
1.8 | As a logged in reviewer I should be able to accept/reject to either complete the process or return it for modification to the lawyer. | 3 | mariam | Sama | Aliaa
1.9 | As a logged in investor i should be able to upload documents to be able to submit the necessary documents | 3 | mariam | Sama | Aliaa
2 | As a logged in lawyer i should be able to add comments to notify the investor of what is wrong with their form | 5 | Ghallab | Sama | Aliaa
2.1 | Create/ Read (Admin) | 5 | Mariam | Sama | Farah
2.2 | Create/ Read (SSC FORM) | 5 | Aliaa | Sama | Farah
2.3 | Create/ Read (SPC FORM) | 5 | Sarah | Sama | Farah
2.4 | Create/ Read (investor) | 5 | Farah | Sama | Farah
2.5 | Create/ Read (Lawyer) | 5 | Norhan | Sama | Farah
2.6 | Create/ Read (Reviewer) | 5 | Menna | Sama | Farah
2.7 | Update/Delete (Admin) | 5 | Mohamed Ghallab | Sama | Farah
2.8 | Update/Delete (Lawyer) | 5 | Rawan | Sama | Farah
2.9 | Update/Delete (Reviewer) | 5 | Eyad | Sama | Farah
3 | Update/Delete (Investor) | 5 | Sama | Sama | Farah
3.1 | Update/Delete (SSC FORM) | 5 | Aliaa/Farah | Sama | Farah
3.2 | Update/Delete (SPC FORM) | 5 | Hana | Sama | Farah