## Sheet1
Unique ID | User story | Story Points | Assignee | Depends on | Testing User Story?
1 | As a logged in investor I should be able to fill the form of SSC to be able to establish an SSC (Create) | 13 | sara ,sama |  | should be able to view the form
1.1 | As a logged in investor I should be able to fill the form of SPC to be able to establish a company(Create) | 13 | sara ,sama | 1 | find function to start fill the form
1.2 | As a logged in User in SSC I should be able to delete form (Delete) | 3 | Sara
1.3 | As a logged in User in SPC I should be able to delete form (Delete) | 3 | Rawan
1.4 | As a logged in User in SSC i should be able to review the form to send comments to investor if any or send it directly to the reviewer (Review) | 3 | Hana | 1 | find the comment label in the form
1.5 | As a logged in Lawyer/Investor in SPC i should be able to review the form to send comments to investor if any or send it directly to the reviewer (Review) | 3 | Mariam
1.6 | As a logged in Lawyer/Investor in SSC i should be able to update the form to be able to correct the form according to the comments received (Update) | 13 | Aliaa | 1 | find function that update parts in the form
1.7 | As a logged in Lawyer/Investor in SPC i should be able to update the form to correct the form according to the comments received (Update) | 13 | Aliaa,Hana | 1 | find function to update parts in the form
1.8 | As a logged in investor i should be able to upload documents to be able to submit the necessary documents | 5 | mariam |  | able to upload documents to the form
2.1 | As a logged in reviewer i should be able to read the form only to decide whether to accept/reject | 3 | Hana | 1 | find accept and reject functions
2.2 | As a logged in lawyer i should be able to add comments to notify the investor of what is wrong with their form | 4 | Mohamed |  | find to add comment
2.3 | As a logged in reviewer I should be able to add comments to notify the lawyer of what is wrong with the form | 4 | Mohamed | 1 | find function to add comment
2.4 | Create/ Read (investor) | 8 | Farah |  | find function that create and read all the investor
2.5 | Create/ Read (Lawyer) | 8 | Norhan |  | find function that create and read all the lawyer
2.6 | Create/ Read (Reviewer) | 8 | Menna |  | find function that create and read all the reviewer
2.7 | Update/Delete (Investor) | 8 | Sama | 2.3 | find function that upadate and delete all investor
2.8 | Update/Delete (Lawyer) | 8 | Rawan | 2.4 | find function that upadate and delete all lawyer
2.9 | Update/Delete (Reviewer) | 8 | Eyad | 2.5 | find function that upadate and delete all reviewwer
3 | Create/ Read (Admin) | 8 | Farah
3.1 | Update/Delete (Admin) | 8 | norhan/menna